## Sheet1
Risk category | Factors | Probability | Impact | Score
Financial | New equipment is expensive | 4 | 5 | 4
| Recession | 4 | 4 | 4
| Decline in revenue | 4 | 5 | 3
| High bargain power of buyer | 2 | 3 | 2
| Overseas Government changes | 2 | 3 | 2
Risk category | Factors | Probability | Impact | Score
Knowledge | New systems | 4 | 4 | 4
| Research availability | 5 | 4 | 4
| Project does not incorporate learnings from other brands | 4 | 2 | 3
| misread information from internal research | 5 | 4 | 4
Risk category | Factors | Probability | Impact | Score
Compliance | Buy-in from all internal stakeholders (incl. SMT) | 5 | 4 | 3
| Problems in implementing new pricing strategy | 5 | 5 | 5
| Case not compliant with HCA policy and strategy | 5 | 3 | 2
Risk category | Factors | Probability | Impact | Score
Strategy | Disallignment with HCA | 5 | 3 | 3
| Portfolio change | 3 | 4 | 3
| Competitor changes | 5 | 5 | 4
| Not align with branding strategy | 3 | 3 | 3
Risk category | Factors | Probability | Impact | Score
Project specific | Errors throughout the project | 5 | 5 | 4
| Lack of learnings from previous projects | 4 | 4 | 3
| Conflicts within teams | 1 | 2 | 1
| Inexperience of team members | 1 | 4 | 2
| Pricing strategy not successful in implementation | 1 | 5 | 2

## All Risk Categories
Risk category | Factors | Probability | Impact | Score
Financial | New equipment is expensive | 4 | 5 | 4
| Recession | 4 | 4 | 4
| Decline in revenue | 4 | 5 | 3
| High bargain power of buyer | 2 | 3 | 2
| Overseas Government changes | 2 | 3 | 2
Knowledge | New systems | 4 | 4 | 4
| Research availability | 5 | 4 | 4
| Project does not incorporate learnings from other brands | 4 | 2 | 3
| misread information from internal research | 5 | 4 | 4
Compliance | Buy-in from all internal stakeholders (incl. SMT) | 5 | 4 | 3
| Problems in implementing new pricing strategy | 5 | 5 | 5
| Case not compliant with HCA policy and strategy | 5 | 3 | 2
Strategy | Disallignment with HCA | 5 | 3 | 3
| Portfolio change | 3 | 4 | 3
| Competitor changes | 5 | 5 | 4
| Not align with branding strategy | 3 | 3 | 3
Project specific | Errors throughout the project | 5 | 5 | 4
| Lack of learnings from previous projects | 4 | 4 | 3
| Conflicts within teams | 1 | 2 | 1
| Inexperience of team members | 1 | 4 | 2
| Pricing strategy not successful in implementation | 1 | 5 | 2
All Risk Categories
The Bubble Chart on top was created using data from each category. There are 5 charts, each one over another using different colours. This is a very time consuming exercise and may not be how you would want this done. I think though, that it is a more accurate representation of all the risk categories put together.
The Bubble Chart on the left was created using data from C2:E22