## DashBoard
Project Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Resource Work
Project Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Helper
Task | Task Name | Work | Duration | Start Date | Finish Date | Resource
Move Office | Empty old office | 32 | 4 | 2014-01-27 08:00 | 2014-01-31 08:00 | Logistics
Move Office | Pack documents | 16 | 2 | 2014-01-27 08:00 | 2014-01-29 08:00 | Logistics
Move Office | Pack IT | 16 | 2 | 2014-01-27 08:00 | 2014-01-29 08:00 | IT Support
Move Office | Pack furnitures | 16 | 2 | 2014-01-29 08:00 | 2014-01-31 08:00 | IT Support
Move Office | Transport | 24 | 3 | 2014-01-29 12:00 | 2014-02-01 12:00 | Logistics
Move Office | Transport documents | 8 | 1 | 2014-01-29 12:00 | 2014-01-30 12:00 | Logistics
Move Office | Transport IT | 8 | 1 | 2014-01-29 12:00 | 2014-01-30 12:00 | Logistics | Row Labels | Sum of Start Date | Sum of Duration | Row Labels | Sum of Work
Move Office | Transport Furnitures | 8 | 1 | 2014-01-31 08:00 | 2014-02-01 08:00 | Logistics | the legals | 41742 | 2 | Finance | 40
Move Office | The new office | 24 | 3 | 2014-02-03 08:00 | 2014-02-06 08:00 | Project Manager | Set objectives | 41730 | 3 | Legal | 16
Move Office | Unpack furnitures | 8 | 1 | 2014-02-03 08:00 | 2014-02-04 08:00 | Logistics | Set a budget | 41734 | 5 | Marketing | 72
Move Office | Unpack IT | 16 | 2 | 2014-02-04 08:00 | 2014-02-06 08:00 | IT Support | Research your customers | 41730 | 5 | Project Manager | 136
Move Office | Unpack documents | 8 | 1 | 2014-02-04 08:00 | 2014-02-05 08:00 | Logistics | Project the right image | 41740 | 4 | Grand Total | 264
Plan Marketing Campaign | Set objectives | 24 | 3 | 2014-04-01 | 2014-04-04 | Project Manager | Monitor and measure | 41744 | 3
Plan Marketing Campaign | Research your customers | 40 | 5 | 2014-04-01 | 2014-04-06 | Marketing | Evaluate the competition | 41732 | 4
Plan Marketing Campaign | Evaluate the competition | 32 | 4 | 2014-04-03 | 2014-04-07 | Project Manager | Develop the right messages | 41738 | 3
Plan Marketing Campaign | Set a budget | 40 | 5 | 2014-04-05 | 2014-04-10 | Finance | Consider communication channels | 41736 | 4
Plan Marketing Campaign | Consider communication channels | 32 | 4 | 2014-04-07 | 2014-04-11 | Project Manager | Grand Total | 375626 | 33
Plan Marketing Campaign | Develop the right messages | 24 | 3 | 2014-04-09 | 2014-04-12 | Project Manager
Plan Marketing Campaign | Project the right image | 32 | 4 | 2014-04-11 | 2014-04-15 | Marketing
Plan Marketing Campaign | the legals | 16 | 2 | 2014-04-13 | 2014-04-15 | Legal
Plan Marketing Campaign | Monitor and measure | 24 | 3 | 2014-04-15 | 2014-04-18 | Project Manager
Formulas:
Finish Date = [Start Date]+[Duration]