## DashBoard
Project Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Resource Work
Project Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Helper
Task | Task Name | Work | Duration | Start Date | Finish Date | Resource
Move Office | Empty old office | 32 | 4 | 2014-01-27 08:00 | 2014-01-31 08:00 | Logistics
Move Office | Pack documents | 16 | 2 | 2014-01-27 08:00 | 2014-01-29 08:00 | Logistics
Move Office | Pack IT | 16 | 2 | 2014-01-27 08:00 | 2014-01-29 08:00 | IT Support
Move Office | Pack furnitures | 16 | 2 | 2014-01-29 08:00 | 2014-01-31 08:00 | IT Support
Move Office | Transport | 24 | 3 | 2014-01-29 12:00 | 2014-02-01 12:00 | Logistics
Move Office | Transport documents | 8 | 1 | 2014-01-29 12:00 | 2014-01-30 12:00 | Logistics
Move Office | Transport IT | 8 | 1 | 2014-01-29 12:00 | 2014-01-30 12:00 | Logistics |  | Data |  | Resource | Sum of Work
Move Office | Transport Furnitures | 8 | 1 | 2014-01-31 08:00 | 2014-02-01 08:00 | Logistics | Task Name | Sum of Start Date | Sum of Duration | Finance | 40
Move Office | The new office | 24 | 3 | 2014-02-03 08:00 | 2014-02-06 08:00 | Project Manager | Unpack IT | 2014-02-04 08:00 | 2 | IT Support | 48
Move Office | Unpack furnitures | 8 | 1 | 2014-02-03 08:00 | 2014-02-04 08:00 | Logistics | Unpack furnitures | 2014-02-03 08:00 | 1 | Legal | 16
Move Office | Unpack IT | 16 | 2 | 2014-02-04 08:00 | 2014-02-06 08:00 | IT Support | Unpack documents | 2014-02-04 08:00 | 1 | Logistics | 112
Move Office | Unpack documents | 8 | 1 | 2014-02-04 08:00 | 2014-02-05 08:00 | Logistics | Transport IT | 2014-01-29 12:00 | 1 | Marketing | 72
Plan Marketing Campaign | Set objectives | 24 | 3 | 2014-04-01 | 2014-04-04 | Project Manager | Transport Furnitures | 2014-01-31 08:00 | 1 | Project Manager | 160
Plan Marketing Campaign | Research your customers | 40 | 5 | 2014-04-01 | 2014-04-06 | Marketing | Transport documents | 2014-01-29 12:00 | 1 | Total Result | 448
Plan Marketing Campaign | Evaluate the competition | 32 | 4 | 2014-04-03 | 2014-04-07 | Project Manager | Transport | 2014-01-29 12:00 | 3
Plan Marketing Campaign | Set a budget | 40 | 5 | 2014-04-05 | 2014-04-10 | Finance | The new office | 2014-02-03 08:00 | 3
Plan Marketing Campaign | Consider communication channels | 32 | 4 | 2014-04-07 | 2014-04-11 | Project Manager | the legals | 2014-04-13 | 2
Plan Marketing Campaign | Develop the right messages | 24 | 3 | 2014-04-09 | 2014-04-12 | Project Manager | Set objectives | 2014-04-01 | 3
Plan Marketing Campaign | Project the right image | 32 | 4 | 2014-04-11 | 2014-04-15 | Marketing | Set a budget | 2014-04-05 | 5
Plan Marketing Campaign | the legals | 16 | 2 | 2014-04-13 | 2014-04-15 | Legal | Research your customers | 2014-04-01 | 5
Plan Marketing Campaign | Monitor and measure | 24 | 3 | 2014-04-15 | 2014-04-18 | Project Manager | Project the right image | 2014-04-11 | 4
[7 empty] | Pack IT | 2014-01-27 08:00 | 2
[7 empty] | Pack furnitures | 2014-01-29 08:00 | 2
[7 empty] | Pack documents | 2014-01-27 08:00 | 2
[7 empty] | Monitor and measure | 2014-04-15 | 3
[7 empty] | Evaluate the competition | 2014-04-03 | 4
[7 empty] | Empty old office | 2014-01-27 08:00 | 4
[7 empty] | Develop the right messages | 2014-04-09 | 3
[7 empty] | Consider communication channels | 2014-04-07 | 4
[7 empty] | Total Result | 875664.5 | 56
Formulas:
Finish Date = [Start Date]+[Duration]