## Dashboard
Projects
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Helper
Task | Task Name | Start Date | Duration | Done days | Not done | % Done
Move Office | Pack documents | 2014-01-27 08:00 | 4 | 1 | 3 | 25% | Row Labels | Sum of Start Date | Sum of Done days | Sum of Not done | Sum of % Done
Move Office | Pack IT | 2014-01-27 08:00 | 4 | 1 | 3 | 25% | Pack IT | 41666.3333 | 1 | 3 | 25%
Move Office | Pack furnitures | 2014-01-29 08:00 | 4 | 0 | 4 | 0% | Pack documents | 41666.3333 | 1 | 3 | 25%
Move Office | Transport documents | 2014-01-29 12:00 | 3 | 0 | 3 | 0% | Pack furnitures | 41668.3333 | 0 | 4 | 0%
Move Office | Transport IT | 2014-01-29 12:00 | 3 | 3 | 0 | 100% | Transport documents | 41668.5 | 0 | 3 | 0%
Move Office | Transport Furnitures | 2014-01-31 08:00 | 3 | 0 | 3 | 0% | Transport IT | 41668.5 | 3 | 0 | 100%
Move Office | Unpack furnitures | 2014-02-03 08:00 | 3 | 0 | 3 | 0% | Transport Furnitures | 41670.3333 | 0 | 3 | 0%
Move Office | Unpack IT | 2014-02-04 08:00 | 4 | 2 | 2 | 50% | Research your customers | 41671 | 3 | 4 | 42.86%
Move Office | Unpack documents | 2014-02-04 08:00 | 3 | 1 | 2 | 33.33% | Set objectives | 41671 | 0 | 5 | 0%
Plan Marketing Campaign | Set objectives | 2014-02-01 | 5 | 0 | 5 | 0% | Evaluate the competition | 41673 | 2 | 4 | 33.33%
Plan Marketing Campaign | Research your customers | 2014-02-01 | 7 | 3 | 4 | 42.86% | Unpack furnitures | 41673.3333 | 0 | 3 | 0%
Plan Marketing Campaign | Evaluate the competition | 2014-02-03 | 6 | 2 | 4 | 33.33% | Unpack IT | 41674.3333 | 2 | 2 | 50%
Plan Marketing Campaign | Set a budget | 2014-02-05 | 7 | 2 | 5 | 28.57% | Unpack documents | 41674.3333 | 1 | 2 | 33.33%
Plan Marketing Campaign | Consider communication channels | 2014-02-07 | 6 | 2 | 4 | 33.33% | Set a budget | 41675 | 2 | 5 | 28.57%
Plan Marketing Campaign | Develop the right messages | 2014-02-09 | 5 | 1 | 4 | 20% | Consider communication channels | 41677 | 2 | 4 | 33.33%
Plan Marketing Campaign | Project the right image | 2014-02-11 | 6 | 2 | 4 | 33.33% | Develop the right messages | 41679 | 1 | 4 | 20%
Plan Marketing Campaign | the legals | 2014-02-13 | 4 | 0 | 4 | 0% | Recrut | 41680 | 2 | 8 | 20%
Plan Marketing Campaign | Monitor and measure | 2014-02-15 | 5 | 1 | 4 | 20% | Project the right image | 41681 | 2 | 4 | 33.33%
New Sales Team | Recrut | 2014-02-10 | 10 | 2 | 8 | 20% | the legals | 41683 | 0 | 4 | 0%
New Sales Team | Interviews | 2014-02-14 | 4 | 1 | 3 | 25% | Interviews | 41684 | 1 | 3 | 25%
New Sales Team | Second round | 2014-02-16 | 2 | 0 | 2 | 0% | Monitor and measure | 41685 | 1 | 4 | 20%
New Sales Team | Test | 2014-02-20 | 1 | 0 | 1 | 0% | Second round | 41686 | 0 | 2 | 0%
New Sales Team | Contract | 2014-02-22 | 1 | 0 | 1 | 0% | Test | 41690 | 0 | 1 | 0%
New Sales Team | Training | 2014-02-24 | 3 | 1 | 2 | 33.33% | Contract | 41692 | 0 | 1 | 0%
[7 empty] | Training | 41694 | 1 | 2 | 33.33%
[7 empty] | Grand Total | 1000251.3333 | 25 | 78 | 523.1%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.